Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | June 20 2026 |
| --- | --- |
| Team ID | SB_2026_NutriAssist_01 |
| Project Name | NutriAssist — Personalized Nutrition Assistant |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration & Onboarding | USN-1 | As a user, I can register for the application by entering my name, email, and password. | 2 | High | V.Yoga Priya |
| Sprint-1 |  | USN-2 | As a user, I can build my health profile (age, gender, height, weight, activity level, goal, dietary restrictions) so my targets are personalized. | 3 | High | P.Chethana Reddy |
| Sprint-1 | Login & Security | USN-3 | As a user, I can log into the application by entering my email and password and receive a JWT for authenticated access. | 2 | High | V.Yoga Priya |
| Sprint-1 |  | USN-4 | As a user, my password is stored securely (hashed with bcrypt) so my credentials are protected. | 1 | High | P.Chethana Reddy |
| Sprint-2 | Personalized Recommendations | USN-5 | As a user, I can calculate my BMR and TDEE (Mifflin-St Jeor formula) based on my profile so I know my energy needs. | 3 | High | P.Chethana Reddy |
| Sprint-2 |  | USN-6 | As a user, I can preview and save goal-adjusted daily calorie and macro (protein/carbs/fat) targets to my profile. | 2 | High | V.Yoga Priya |
| Sprint-2 | Meal Logging | USN-7 | As a user, I can search a food database and log a meal with quantity scaled per gram. | 3 | High | V.Yoga Priya |
| Sprint-2 |  | USN-8 | As a user, I can view, filter, and delete my logged meal entries for any given date. | 2 | Medium | P.Chethana Reddy |
| Sprint-3 | Tracking Dashboard | USN-9 | As a user, I can see a dashboard comparing today's calories/macros against my targets. | 3 | High | V.Yoga Priya |
| Sprint-3 |  | USN-10 | As a user, I can view a 7-day calorie chart so I can track my progress over time. | 2 | Medium | V.Yoga Priya |
| Sprint-3 | Recipes & Grocery List | USN-11 | As a user, I can browse recipe suggestions filtered by meal type and my goal. | 2 | Medium | P.Chethana Reddy |
| Sprint-3 |  | USN-12 | As a user, I can generate an aggregated grocery list from the recipes I select. | 3 | Medium | P.Chethana Reddy |
| Sprint-4 | Educational Resources | USN-13 | As a user, I can read articles on nutrition fundamentals to make more informed choices. | 1 | Low | V.Yoga Priya |
| Sprint-4 |  | USN-14 | As a user, I can browse a directory of nutrition professionals for further guidance. | 1 | Low | P.Chethana Reddy |
| Sprint-4 | Deployment & Quality | USN-15 | As a developer, I can seed the food and recipe databases so the app has starter data for local development. | 1 | Low | P.Chethana Reddy |
| Sprint-4 |  | USN-16 | As a developer, I can manually test each user flow end-to-end (register → login → targets → log meals → dashboard → recipes → grocery list) to verify quality before release. | 2 | Medium | V.Yoga Priya |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date (Planned) | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 8 | 6 Days | 20 Jun 2026 | 26 Jun 2026 | 8 | 26 Jun 2026 |
| Sprint-2 | 10 | 4 Days | 26 Jun 2026 | 30 Jun 2026 | 10 | 30 Jun 2026 |
| Sprint-3 | 10 | 3 Days | 1 Jul 2026 | 3 Jul 2026 | 10 | 3 Jul 2026 |
| Sprint-4 | 5 | 5 Days | 4 Jul 2026 | 9 Jul 2026 | 5 | 9 Jul 2026 |

Velocity:

Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts